Table of Contents

| # | Title | Page |
| --- | --- | --- |
|  | Introduction - Project Overview | 02 To 03 |
|  | Background & Rationale - Background & Rationale | 03 To 04 |
|  | Objectives & Achievements - Goals, Key Outcomes, Summary Metrics | 05 To 06 |
|  | Geographic Coverage - District-wise Implementation & Impact | 06 To 07 |
|  | SDG Alignment - SDGs 4, 7, 12, 13 Contributions | 08 To 09 |
|  | Implementation Activities - Assessment, Design, Installation, Training, District-wise Coverage of 84 Schools | 10 To 16 |
|  | Challenges & Learnings - Field Realities and Key Takeaways | 17 To 17 |
|  | Financial Summary - Budget Allocation, Utilization & Variance | 18 To 19 |
|  | Project Outcomes - Education Access, Cost Savings, Energy Use | 20 To 21 |
|  | Impact Overview - Infrastructure enhancement, rural empowerment, and clean energy leadership | 21 To 22 |
|  | Project Sustainability and Carbon Footprint - CO₂ Reduction & Long-term Benefits | 23 To 27 |
|  | Testimonials & Case Study - Voices from Schools | 28 To 29 |
|  | Annexures - Designs, Photos, Audited Utilisation Certificate, Letters | 30 To 51 |

- INTRODUCTION

  - Project Overview

The School Infrastructure Project was conceptualized and implemented with the generous support of Motilal Oswal, with the aim of addressing critical infrastructure and learning gaps in rural and semi-urban schools across Maharashtra. The project recognized that quality education is not only dependent on curriculum delivery but also on the availability of enabling infrastructure such as digital tools, reliable electricity, safe sanitation facilities, and a supportive ecosystem for both students and teachers.

In many government and aided schools, especially in rural regions, traditional teaching methods continue to dominate due to the lack of access to modern educational technology. Additionally, frequent power outages disrupt learning continuity, while inadequate sanitation facilities—particularly for adolescent girls—impact attendance and overall well-being. At the same time, communities surrounding these schools, including vulnerable elderly populations, often lack access to basic healthcare services. This project was therefore designed as a holistic intervention, addressing multiple interconnected challenges within the education ecosystem.

The project focused on four key pillars:

- Digital Learning Enhancement:

Introduction of digital interactive panels and smart classroom solutions enabled students from Grade 1 to Grade 7 to access Maharashtra State Board curriculum through audio-visual and interactive content. This significantly improved classroom engagement, conceptual understanding, and participation.

- Energy Access through Solar Systems:

To address the challenge of unreliable electricity, the project included the repair, restoration, and activation of off-grid 5KVA solar power systems in selected schools. This ensured uninterrupted power supply for classrooms, digital equipment, and basic school operations, thereby creating a stable and conducive learning environment.

- Sanitation & Hygiene Improvement:

Installation of incinerator machine in school helped improve menstrual hygiene management for girl students. This intervention  promoted dignity, reduced absenteeism, and encouraged continued education among adolescent girls.

- Community Health & Institutional Strengthening:

Extending beyond school infrastructure, the project also integrated elderly care support in nearby urban slum communities through home visits, health check-ups, assistive devices, and linkages to social welfare schemes. Additionally, institutional strengthening was undertaken through the redesign and development of MASHAL’s digital presence, ensuring better outreach and long-term sustainability.

Despite its short duration of three months (January to March 2026), the project achieved significant outcomes by adopting a targeted, need-based, and time-bound implementation approach. Activities were executed efficiently across multiple districts, ensuring that each intervention was aligned with the specific needs of the schools and communities.

Overall, the project not only improved physical infrastructure but also transformed the learning experience, empowered teachers with new skills, enhanced student engagement, and strengthened community well-being. It stands as a replicable model demonstrating how integrated infrastructure interventions can drive meaningful and sustainable change in the education sector.

- BACKGROUND AND RATIONALE

  - Background & Rationale

Across rural and semi-urban regions of Maharashtra, government and aided schools play a critical role in providing foundational education to children from economically and socially vulnerable communities. However, despite ongoing efforts by the government, many of these schools continue to face systemic infrastructure and capacity-related challenges that limit the quality of education delivered.

One of the most prominent gaps is the limited access to digital learning tools. While urban schools are rapidly adopting smart classrooms and interactive teaching methodologies, rural schools often rely on traditional chalk-and-board methods. This restricts students’ exposure to visual and experiential learning, which is increasingly essential for improving comprehension, especially in subjects such as mathematics, science, and languages. The absence of digital tools also widens the urban-rural education divide, leaving rural students at a disadvantage in a technology-driven world.

Another critical challenge is the unreliable electricity supply. Frequent power cuts and voltage fluctuations disrupt daily classroom activities and make it difficult to use even basic electrical equipment. In many schools, previously installed digital infrastructure remains underutilized or non-functional due to the lack of a stable power source. This not only leads to resource wastage but also discourages teachers from adopting digital teaching practices.

The issue of inadequate sanitation facilities, particularly for adolescent girls, further compounds the problem. Lack of proper menstrual hygiene management systems, such as safe disposal mechanisms, often leads to discomfort, absenteeism, and in some cases, school dropouts among girl students. Ensuring access to safe and dignified sanitation facilities is therefore essential for promoting gender equity in education.

In addition to infrastructure gaps, there is also a significant need to strengthen teacher capacity in technology-based education. Many teachers in rural schools have limited exposure to digital tools and require training and continuous support to effectively integrate technology into their teaching practices. Without adequate training, even well-equipped classrooms may fail to deliver the intended impact.

Beyond the school environment, surrounding communities—especially vulnerable groups such as the elderly—often lack access to basic healthcare services and social security schemes. These socio-economic challenges indirectly affect students’ well-being and their ability to focus on education, highlighting the need for a more holistic, community-linked approach.

These interconnected challenges directly impact:

- Learning outcomes, by limiting students’ understanding and retention

- Student engagement, due to lack of interactive and stimulating teaching methods

- Attendance and retention, especially among girls

- Teacher effectiveness, due to limited exposure to modern pedagogies

Recognizing these gaps, the School Infrastructure Project was designed as an integrated intervention model aimed at strengthening the overall school ecosystem rather than addressing issues in isolation. The project introduced sustainable, technology-driven solutions such as digital classrooms and solar-powered systems, while also focusing on sanitation, teacher training, and community health support.

The rationale behind this approach was to ensure that improvements are:

- Holistic – addressing multiple dimensions of the education ecosystem

- Sustainable – leveraging renewable energy and capacity building

- Inclusive – benefiting students, teachers, and the wider community

- Scalable – creating a model that can be replicated in other regions

By bridging the digital and infrastructure divide, the project aimed to create an enabling environment where students can learn more effectively, teachers can teach more innovatively, and schools can function as centres of community development.

- PROJECT OBJECTIVES, & ACHIEVEMENTS

The School Infrastructure Project was designed with a set of clearly defined objectives aimed at addressing critical gaps in rural education and community well-being. These objectives were not only focused on infrastructure development but also on creating long-term, sustainable impact through capacity building and integrated interventions.

  - Project Goals

    - To enhance digital learning infrastructure in rural schools

A key objective of the project was to transform traditional classrooms into interactive learning environments by introducing digital tools such as smart panels and digital classroom systems. These tools were aligned with the Maharashtra State Board curriculum, enabling students from primary grades to access subject content through engaging audio-visual formats. The goal was to improve comprehension, increase student participation, and make learning more enjoyable and effective.

    - To ensure uninterrupted power supply through solar systems

Recognizing that inconsistent electricity is a major barrier in rural schools, the project aimed to restore and activate off-grid solar power systems. By doing so, schools could operate digital equipment without disruption, ensuring continuity in teaching-learning processes and reducing dependency on unreliable grid electricity.

    - To improve sanitation facilities for girl students’

The project prioritized menstrual hygiene management by installing incinerator machines in schools. This intervention aimed to create a safe and dignified environment for adolescent girls, reduce absenteeism, and promote gender-sensitive infrastructure within schools.

    - To strengthen teacher capacity in digital education

Introducing digital tools alone is not sufficient without equipping teachers with the necessary skills. Therefore, the project focused on capacity building through hands-on training sessions, enabling teachers to effectively use digital platforms, troubleshoot minor technical issues, and integrate technology into their daily lesson plans.

    - To support community well-being through health interventions

Understanding the strong link between community health and education, the project extended support to vulnerable elderly populations through home-based healthcare services, health check-ups, assistive devices, and social scheme linkages. This holistic approach ensured that the benefits of the project extended beyond schools into the broader community.

  - Key Outcomes

The project successfully translated its objectives into measurable outcomes within a short span of three months:

- Digital Classrooms Established in 3 Schools: Fully functional digital learning systems were installed, benefiting students from Grade 1 to Grade 7. These classrooms are now being used regularly to deliver curriculum-based interactive lessons.

- Solar Systems Restored in 5 Schools: Previously non-functional or underperforming solar units were repaired and activated, ensuring a reliable and sustainable energy source for school operations and digital infrastructure.

- Sanitation Support Provided in 1 School: An incinerator machine was installed to address menstrual hygiene needs, significantly improving the school environment for girl students.

- Elderly Healthcare Support Extended to 4200+ Beneficiaries: Through home visits and healthcare services in Pune’s urban slums, elderly individuals received essential medical support and were connected to relevant social welfare schemes.

  - Summary Metrics

The project achieved substantial outreach and impact, as reflected in the following metrics:

- Total Schools Covered: 9

The project reached schools across multiple districts, ensuring a geographically diverse and inclusive implementation.

- Total Students Benefited: 1,517+

Students across primary grades gained access to improved learning environments, digital content, and better infrastructure, leading to enhanced educational experiences.

- Girl Students Benefited (Sanitation): 162

The installation of sanitation facilities directly supported adolescent girls, contributing to improved attendance, confidence, and dignity.

- Elderly Beneficiaries: 4200+

A significant number of elderly individuals benefited from healthcare services, reflecting the project’s broader commitment to community development.

  - Overall Achievement Perspective

The project stands out for its integrated and multi-sectoral impact, successfully combining education, energy, sanitation, and healthcare interventions. Despite the short implementation period, it delivered high-impact, measurable outcomes by focusing on need-based planning, efficient execution, and stakeholder engagement.

Importantly, the achievements are not just quantitative but also qualitative:

- Classrooms have become more interactive and engaging

- Teachers are more confident in using technology

- Schools now have sustainable energy solutions

- Girls experience a more inclusive and supportive environment

- Communities feel more connected and supported

These outcomes collectively contribute to building a stronger, more resilient, and future-ready rural education ecosystem.

- GEOGRAPHIC COVERAGE

The School Infrastructure Project was implemented across multiple districts of Maharashtra, ensuring a diverse geographic reach covering rural, semi-urban, and urban vulnerable communities. The district-wise approach enabled the project to respond to localized needs, ensuring that each intervention was relevant, targeted, and impactful.

  - Pune District (Urban Slums)

In Pune district, the project focused on both school infrastructure strengthening and community health support.

- Schools Covered: 1

- Key Intervention: Solar system repair and activation

At the school level, the restoration of the solar power system ensured uninterrupted electricity supply, which is critical for running classrooms efficiently, especially where grid power is inconsistent. This intervention has enabled the school to function smoothly and supports the use of any existing or future digital infrastructure.

In addition, the project extended beyond schools into urban slum areas of Warje and Kothrud, where:

- 4200+ elderly individuals received healthcare support

- Services included home visits, health check-ups, assistive devices, and linkages to government schemes

This dual approach in Pune reflects the project’s commitment to integrated development, connecting education with community well-being.

  - Satara District

Satara emerged as a major focus area of the project, with multiple schools benefiting from both digital and energy interventions.

- Schools Covered: 4

- Key Interventions: Digital classrooms and solar system repair

In this district:

- 1 School were equipped with digital classroom solutions, enabling students to access curriculum-based interactive learning

- Existing 3 schools’ solar systems were repaired and reactivated, ensuring consistent power supply

This combination of digital and energy support created a complete ecosystem for modern education, where technology could be effectively utilized without interruption. The interventions have significantly improved classroom engagement, teaching efficiency, and school functionality.

  - Nashik District

In Nashik, the project focused on introducing digital learning infrastructure in a targeted manner.

- Schools Covered: 1

- Key Intervention: Digital classroom

The installation of a digital classroom transformed the traditional teaching approach into a more interactive and student-friendly experience. Students now benefit from audio-visual learning, which enhances understanding and retention. Teachers have also adopted more innovative teaching methods, making lessons more engaging.

  - Ahilyanagar District

Ahilyanagar district witnessed a combination of educational and sanitation-focused interventions, addressing both learning and gender-specific needs.

- Schools Covered: 2

- Key Interventions: Incinerator installation and digital classroom

Key impacts include:

- Installation of an incinerator machine in 1 school to support menstrual hygiene management for girl students, promoting dignity, hygiene, and regular school attendance

- Introduction of a digital classroom in 1 school, enhancing the quality of education through technology-enabled teaching

This integrated approach ensured that both academic and social barriers to education were addressed effectively.

  - Overall Geographic Impact

The district-wise implementation strategy ensured that:

- Interventions were need-based and context-specific

- Resources were utilized efficiently across locations

- Both educational institutions and surrounding communities benefited

By covering multiple districts with varied interventions, the project successfully demonstrated a scalable and adaptable model that can be replicated in other regions. It also highlighted the importance of combining infrastructure, technology, and community support to create sustainable and long-term impact.

- SDG ALIGNMENT

The School Infrastructure Project strongly aligns with multiple United Nations Sustainable Development Goals (SDGs) by addressing interconnected challenges related to education, health, gender, energy, and community development. The project’s integrated approach ensured that each intervention contributed meaningfully to achieving broader global development priorities.

The project contributed to improving health outcomes at both the school and community levels.

- Elderly Healthcare Support:

More than 4200 elderly individuals in urban slum areas received home-based healthcare services, including regular health check-ups, assistive devices, and linkages to government health and social security schemes. This improved their access to essential healthcare and enhanced their quality of life.

- School Health & Hygiene:

Installation of incinerators promoted safe menstrual hygiene practices among adolescent girls, reducing health risks and absenteeism.

Impact:
Improved physical well-being, increased access to healthcare services, and enhanced hygiene practices.

SDG 3

GOOD HEALTH AND WELL - BEING

This was the core focus of the project.

- Digital Classrooms:

Introduction of interactive digital panels enabled students to learn through audio-visual content aligned with the Maharashtra State Board curriculum.

- Teacher Training:

Capacity-building sessions empowered teachers to adopt modern, technology-driven teaching methodologies.

- Improved Learning Environment:

Reliable electricity through solar systems ensured uninterrupted teaching and learning processes.

Impact:

Enhanced student engagement, improved learning outcomes, and strengthened teaching effectiveness

SDG 4

QUALITY EDUCATION

The project addressed gender-specific barriers in education, particularly for adolescent girls.

- Menstrual Hygiene Management:

Installation of incinerator machines provided a safe and dignified solution for sanitary waste disposal.

- Improved School Environment:

Better sanitation facilities encouraged regular attendance among girl students and reduced dropout risks.

Impact:
Promoted dignity, safety, and equal access to education for girls.

SDG 5

GENDER EQUALITY

The project supported renewable energy adoption in schools through solar infrastructure.

- Solar System Repair & Activation:

Off-grid 5KVA solar systems were restored, ensuring a sustainable and cost-effective power source.

- Reduced Dependency on Grid Electricity:

Schools became less vulnerable to power cuts and energy-related disruptions.

Impact:
Ensured access to clean, reliable, and sustainable energy, while reducing environmental impact.

SDG 7

AFFORDABLE AND CLEAN ENERGY

The project focused on bridging gaps between urban and rural communities.

- Digital Divide Reduction:

Rural students gained access to digital learning tools similar to those available in urban schools.

- Inclusive Community Support:

Elderly individuals from underserved communities received healthcare and social support.

Impact:
Reduced disparities in education access, healthcare services, and overall quality of life.

SDG 10

REDUCED INEQUALITIES

SDG 11: Sustainable Communities

The project contributed to building resilient and inclusive communities.

- Strengthened School Infrastructure:

Schools were transformed into better-equipped, future-ready learning spaces.

- Community Linkages:

Health interventions and awareness strengthened community engagement and support systems.

- Sustainable Solutions:

Use of solar energy and durable infrastructure ensured long-term benefits.

Impact:
Enhanced community resilience, improved living standards, and promoted sustainable development practices.

SDG 11

SUSTAINABLE COMMUNITIES

  - Overall SDG Contribution

By aligning with multiple SDGs, the project demonstrated a holistic development model where:

- Education is supported by infrastructure and technology

- Health and hygiene are integrated into school ecosystems

- Clean energy enables sustainability

- Community well-being strengthens long-term impact

This multi-dimensional approach ensures that the outcomes are not only immediate but also sustainable, scalable, and aligned with global development priorities.

- IMPLEMENTATION ACTIVITIES

The implementation of the School Infrastructure Project was carried out through a structured, multi-stage approach, ensuring that each intervention was need-based, efficient, and sustainable. The activities were carefully planned and executed across districts to maximize impact within the three-month project duration.

  - Assessment

The project began with a comprehensive baseline assessment to understand the existing conditions and identify priority areas for intervention.

- Infrastructure Assessment:

Detailed site visits were conducted in selected schools to evaluate the status of classrooms, availability of electricity, condition of existing solar systems, and sanitation facilities.

- Digital Readiness Evaluation:

Schools were assessed for their readiness to adopt digital learning tools, including availability of space, teacher familiarity with technology, and student needs.

- Gap Identification:
Key gaps identified included:

  - Lack of digital teaching aids

  - Non-functional or underutilized solar systems

  - Absence of proper menstrual hygiene disposal systems

  - Limited teacher capacity in using digital platforms

This assessment phase ensured that interventions were targeted, relevant, and aligned with on-ground realities.

  - Installation & Infrastructure Support

Based on the assessment findings, the project implemented a range of infrastructure improvements:

    - Digital Learning Infrastructure

- Digital interactive panels and smart classroom systems were installed in 3 schools

- Content aligned with the Maharashtra State Board syllabus was integrated for Grades 1 to 7

- Classrooms were transformed into interactive learning spaces, enabling audio-visual and activity-based education

    - Solar Energy Support

- Off-grid 5KVA solar systems in 5 schools were repaired, restored, and activated

- Technical repairs included fixing panels, inverters, batteries, and wiring systems

- Schools now benefit from reliable and uninterrupted electricity, supporting both academic and administrative functions

    - Sanitation Infrastructure

- An incinerator machine was installed to support menstrual hygiene management for girl students

- The facility ensures safe and hygienic disposal of sanitary waste, contributing to a more inclusive school environment

  - Training & Capacity Building

Recognizing that infrastructure alone cannot drive change, the project placed strong emphasis on teacher training and capacity building.

- Digital Teaching Methods:

Teachers were trained on how to effectively use digital content to make lessons more engaging and interactive.

- Technical Troubleshooting:

Basic troubleshooting skills were provided to ensure teachers can independently manage minor technical issues related to digital equipment.

- Curriculum Integration:

Training sessions focused on aligning digital tools with the Maharashtra State Board syllabus, ensuring that technology complements regular teaching practices.

- Hands-on Approach:

Practical demonstrations and interactive sessions helped build confidence among teachers, encouraging long-term adoption of digital teaching methods.

  - District-wise School Coverage

    - Digital Classrooms

Digital learning solutions were successfully implemented in the following schools:

- ZP Primary School, Mandave Kh, Ahilyanagar (Ahilyanagar District)

  - Students Benefited: 182

  - Impact: Enhanced classroom engagement and improved conceptual understanding

- ZP Primary School, Savargaon (Nashik District)

  - Students Benefited: 102

  - Impact: Transition from traditional to digital learning methods

- ZP Primary School, Angapur No-2 (Satara District)

  - Students Benefited: 84

  - Impact: Improved participation and learning outcomes

    - Solar Infrastructure Support

Solar system repair and activation were carried out in the following schools:

- Yashwantrao Chavan Vidyalay, Bhosari (Pune) – 180 students

- ZP Primary School, Kameri (Satara) – 103 students

- S. Anandrao Ghadge Vidyalay, Kameri (Satara) – 118 students

- New English School, Angapur (Satara) – 285 students

- New English School, Chinchner Vandan (Satara) – 175 students

Impact:

- Ensured uninterrupted electricity supply

- Enabled effective use of digital classrooms

- Improved overall school functioning

    - Sanitation Support

- Mulakhore Vidyalay, Mandave Bk (Ahilyanagar District)

  - Total Students: 288

  - Girl Students Benefited: 162

Impact:

- Improved menstrual hygiene management

- Increased comfort, dignity, and school attendance among girls

    - Community Health Support

- Location: Warje & Kothrud (Pune Urban Slums)

- Beneficiaries: 4200+ elderly individuals

Services Provided:

- Home visits and regular health check-ups

- Distribution of assistive devices

- Linkages to government health and social security schemes

Impact:

- Improved access to healthcare

- Enhanced quality of life for elderly populations

- Strengthened community trust and engagement

    - Digital Strengthening (Institutional Development)

- Ongoing redesign and development of MASHAL’s website

- Regular monitoring and review of design and functionality

Impact:

- Improved organizational visibility and outreach

- Strengthened communication with stakeholders and donors

- Enhanced digital presence for long-term sustainability

  - Overall Implementation Approach

The project’s implementation was guided by:

- Need-based planning

- Timely execution within a short duration

- Close coordination with schools and communities

- Focus on sustainability and capacity building

By combining infrastructure development, training, and community engagement, the project ensured that the interventions are not only effective in the short term but also sustainable in the long run.

  - Input/ Output/Outcome

| Sr. No. | Intervention Area | Inputs (Resources Invested) | Outputs (Immediate Results) | Outcomes (Short to Medium Term Impact) |
| --- | --- | --- | --- | --- |
| 1 | Assessment & Planning | Baseline surveys, field visits, technical assessments, staff time | Needs assessment completed for selected schools and communities | Targeted and need-based interventions ensuring efficient resource utilization |
| 2 | Digital Learning Infrastructure | Digital interactive panels, software content (Maharashtra Board), installation support | 3 schools equipped with digital classrooms; 368+ students directly reached | Improved student engagement, better conceptual understanding, enhanced learning outcomes |
| 3 | Solar Infrastructure Support | Technical experts, repair materials (panels, batteries, wiring), logistics | 5 schools with repaired and functional 5KVA off-grid solar systems; 770+ students benefited | Uninterrupted power supply, improved classroom continuity, increased utilization of digital tools |
| 4 | Sanitation Support (Girls) | Incinerator machine, installation support, awareness inputs | 1 school equipped with incinerator; 162 girl students benefited | Improved menstrual hygiene management, increased attendance and dignity for girl students |
| 5 | Teacher Training & Capacity Building | Training modules, expert trainers, digital content orientation sessions | Teachers trained in digital teaching, troubleshooting, and curriculum integration | Increased teacher confidence, effective use of digital tools, improved teaching quality |
| 6 | Community Health (Elderly Care) | Health professionals, assistive devices, outreach teams, coordination support | 4200+ elderly received home visits, health check-ups, and scheme linkages | Improved health access, enhanced quality of life, strengthened community trust |
| 7 | Institutional Strengthening (Website Development) | Technical team, design tools, monitoring efforts | Website redesign and development in progress | Improved digital presence, better stakeholder communication, enhanced organizational visibility |
| 8 | Project Management & Coordination | Project team (managers, engineers, coordinators), travel, monitoring tools | Smooth implementation across 4 districts within 3 months | Timely delivery, effective coordination, scalable and replicable project model |

  - District Wise Schools List

The following is the district wise list of 9 schools across Maharashtra where repair and activation of off grid mono panel solar system and digital interactive panel units have been successfully installed by MASHAL:

| Sr. No | Name of the School | Intervention | District |
| --- | --- | --- | --- |
| 1 | ZP Primary School, Mandave Kh, Ahilyanagar | Installation of Digital learning solutions | Ahilyanagar |
| 2 | ZP Primary School, Savargaon, Sangamner, Nashik | Installation of Digital learning solutions | Nashik |
| 3 | ZP Primary School, Angapur No-2, Satara | Installation of Digital learning solutions | Satara |
| 4 | Mulakhore Vidyalay, Mandave Bk, Ahilyanagar | Installation of Incinerator for Girls | Ahilyanagar |
| 5 | Yashwantrao Chavan Vidyalay, Bhosari, Pune | Solar System Repair & Activation | Pune |
| 6 | ZP Primary School, Kameri, Satara | Solar System Repair & Activation | Satara |
| 7 | New English School, Angapur, Satara | Solar System Repair & Activation | Satara |
| 8 | S. Anandrao Ghadge Vidyalay, Kameri, Satara | Solar System Repair & Activation | Satara |
| 9 | New English School, Chinchner Vandan, Satara | Solar System Repair & Activation | Satara |

- CHALLENGES & LEARNINGS

The implementation of the School Infrastructure Project across multiple districts within a short time frame provided valuable insights into on-ground realities. While the project achieved its intended objectives, several operational and contextual challenges were encountered. These challenges also led to important learnings that will guide future program design and implementation.

  - Key Challenges

    - Technical Issues in Old Solar Systems

Several schools had previously installed solar systems that were non-functional or partially operational due to:

- Battery degradation and poor maintenance

- Faulty wiring and inverter issues

- Lack of regular servicing and technical oversight

Reviving these systems required additional technical effort, time, and resources, sometimes beyond initial estimates.

    - Connectivity Limitations in Rural Areas

In remote locations, internet connectivity was either weak or inconsistent, which posed challenges such as:

- Difficulty in accessing updated digital content

- Limited scope for real-time troubleshooting or remote support

- Reduced effectiveness of certain digital learning features

This emphasized the need for offline-compatible solutions in rural settings.

    - Coordination Across Multiple Districts within a Short Duration

The project was implemented across Pune, Satara, Nashik, and Ahilyanagar districts within a tight three-month timeline. This created challenges in:

- Managing logistics and transportation of equipment

- Coordinating with multiple schools and local stakeholders

- Ensuring timely installation, training, and follow-ups

Efficient coordination required strong project management and continuous monitoring.

  - Key Learnings

    - Local Technician Support Ensures Sustainability

The sustainability of infrastructure, especially solar systems and digital equipment, depends heavily on local technical support:

- Availability of trained local technicians enables quick repairs

- Reduces downtime of systems

- Builds local ownership and reduces dependency on external experts

This approach ensures long-term functionality and cost-effectiveness.

    - Training is as Important as Infrastructure

The project reinforced that infrastructure alone does not guarantee impact. Equal emphasis must be placed on:

- Capacity building of teachers

- Practical, hands-on training sessions

- Simplifying technology for easy adoption

When teachers are confident and skilled, the utilization and impact of infrastructure increase significantly.

    - Community Engagement Enhances Project Ownership

Active involvement of school management committees, local leaders, and community members proved crucial:

- Increased acceptance and support for project activities

- Better maintenance and safeguarding of installed infrastructure

- Stronger accountability and ownership at the local level

Community engagement ensures that the benefits of the project are sustained beyond the implementation period.

  - Overall Reflection

The challenges encountered during the project were not just obstacles but opportunities for learning and improvement. They highlighted the importance of adopting a holistic and adaptive approach, where infrastructure development is complemented by capacity building, local engagement, and sustainability planning.

These learnings will play a critical role in strengthening future interventions, making them more resilient, scalable, and impactful across diverse geographies.

- FINANCIAL SUMMARY

| Sr. No | Particulars | Total Proposed Budget | Total Expenditure | % of Total Expenditure of Proposed Budget |
| --- | --- | --- | --- | --- |
| 1 | Planning and Need Assessment | 45,999 | 48,316 | 04.83% |
| 2 | Qualitative & Digital Education | 3,48,750 | 3,48,750 | 34.87% |
| 3 | School Infrastructure Improvement Support | 1,15,800 | 1,15,800 | 11.58% |
| 4 | Elderly Care Health Improvement Support | 2,60,400 | 2,60,400 | 26.05% |
| 5 | Strengthen & Development of MASHAL's Website | 1,06,200 | 1,06,200 | 10.62% |
| 6 | Program Support Cost | 75,232 | 72,915 | 07.29% |
| 7 | Organizational Cost (MASHAL) 5% | 47,619 | 47,619 | 04.76% |
| Total Rs. |  | 10,00,000 | 10,00,000 | 100% |

  - Budget Utilisation

    - Planning and Need Assessment (₹48,316 | 4.83%)

Description: This component covered baseline surveys, field visits, stakeholder consultations, and need assessment exercises across selected project locations. It ensured that interventions were designed based on actual school + community needs and gaps.

Utilisation: The expenditure slightly exceeded the proposed budget due to additional field visits and data validation requirements. Funds were utilized for travel, survey tools, school meetings, and documentation. This investment enabled accurate planning and improved targeting of beneficiaries.

    - Qualitative & Digital Education (₹3,48,750 | 34.87%)

Description: This component focused on enhancing the quality of education through digital learning tools, interactive content, and capacity building of students and teachers.

Utilisation: The budget was fully utilized for procurement and deployment of digital education resources, smart learning tools, and educational content. It also covered training sessions and implementation support, leading to improved student engagement and learning outcomes.

    - School Infrastructure Improvement Support (₹1,15,800 | 11.58%)

Description: This component aimed to strengthen basic school infrastructure, ensuring a safe and conducive learning environment for students.

Utilisation: Funds were fully utilized for, repair & activation of off grid solar systems in schools, and sanitation improvements support. This contributed to better school attendance and improved hygiene conditions for girl students.

    - Elderly Care Health Improvement Support (₹2,60,400 | 26.05%)

Description: This component focused on improving the health and well-being of elderly beneficiaries through regular health check-ups, access to medical services, and support systems.

Utilisation: The entire budget was utilized for organizing health camps, home visits, tele-consultations, medicines, and referrals. The intervention significantly improved access to healthcare and enhanced the quality of life for elderly beneficiaries.

    - Strengthening & Development of MASHAL's Website (₹1,06,200| 10.62%)

Description:

This component aimed at enhancing MASHAL’s digital presence, improving transparency, and strengthening communication with stakeholders through a robust and user-friendly website.

Utilisation: Funds were fully utilized for website redesign, development, content creation, and technical improvements. The upgraded platform now supports better visibility, reporting, and stakeholder engagement.

    - Program Support Cost (₹72,915 | 7.29%)

Description: This includes operational costs required for smooth program implementation such as coordination, communication, logistics, and monitoring.

Utilisation: The expenditure was slightly lower than planned due to cost efficiencies. Funds were used for office supplies, printing, travel, communication, and monitoring activities, ensuring effective and timely execution of all project components.

    - Organizational Cost (MASHAL) – 5% (₹47,619 | 4.76%)

Description: This component covers core organizational expenses required to manage and support the project, including administration, governance, and compliance.

Utilisation: The allocated budget was fully utilized to support essential administrative functions such as finance management, reporting, compliance, and organizational oversight, ensuring accountability and smooth project delivery.

  - Overall Utilisation Summary:

The total project budget of ₹10,00,000 was fully utilized (100%) across all components. Expenditure closely aligned with the proposed allocations, with minor variations reflecting adaptive implementation and efficiency. The financial utilisation demonstrates effective planning, strong execution, and optimal use of resources to achieve project outcomes.

- Approved Budget for Project 			Rs. 10,00,000

- Budget Utilization:					Rs. 10,00,000

- Balance Budget: 					Rs. 0

- OUTCOMES ACHIEVED

The School Infrastructure Project generated significant and multi-dimensional outcomes by addressing key gaps in education, energy, health, and institutional capacity. The interventions not only delivered immediate improvements but also laid the foundation for long-term, sustainable impact across schools and communities.

  - Education Access & Learning Enhancement

One of the most visible outcomes of the project was the transformation in the teaching-learning environment within schools.

- Improved Student Engagement:

The introduction of digital classrooms enabled students to learn through audio-visual content, animations, and interactive modules, making lessons more interesting and easier to understand. Subjects that were previously difficult to grasp became more accessible, leading to higher participation in classrooms.

- Enhanced Teaching Quality:

Teachers adopted innovative teaching methodologies, moving beyond traditional rote learning. Digital tools allowed them to explain concepts more clearly, conduct interactive sessions, and maintain student attention throughout the class.

- Inclusive Learning Environment:

Digital content catered to different learning speeds and styles, ensuring that both fast and slow learners could benefit equally.

Overall Impact:

A shift from passive learning to active, student-cantered education, resulting in better comprehension and retention.

  - Energy Access & School Functionality

Reliable energy supply played a critical role in ensuring the effectiveness of other interventions.

- Uninterrupted Electricity:

The repair and activation of solar systems ensured that schools had consistent power supply, even during grid failures.

- Operational Efficiency:

Classrooms, digital equipment, and administrative functions could operate without disruption, improving overall school efficiency.

- Support for Digital Infrastructure:

Solar energy enabled continuous use of digital classrooms, maximizing the return on investment in educational technology.

Overall Impact:

Creation of a stable and conducive learning environment, reducing dependency on unreliable power sources and supporting sustainable operations.

  - Health & Hygiene Improvement

The project addressed critical health and hygiene needs, particularly for vulnerable groups.

- Menstrual Hygiene Management for Girls:

The installation of incinerator machines provided a safe, hygienic, and private solution for sanitary waste disposal. This significantly improved comfort and confidence among girl students.

- Increased School Attendance:

With improved hygiene facilities, adolescent girls were less likely to miss school during menstruation, contributing to better continuity in education.

- Elderly Healthcare Support:

Through community interventions, elderly individuals received regular health check-ups, assistive devices, and access to social schemes, improving their overall well-being.

Overall Impact:

Improved health outcomes, dignity, and quality of life, both within schools and in surrounding communities.

  - Institutional Strengthening & Capacity Building

The project contributed to strengthening schools as institutions capable of sustaining improvements over time.

- Modernized School Infrastructure:

Schools were equipped with digital classrooms, functional solar systems, and improved sanitation facilities, making them more resilient and future-ready.

- Teacher Empowerment:

Teachers gained practical skills in digital education, enabling them to confidently use technology as a regular part of their teaching process.

- Improved School Reputation:

Enhanced infrastructure and teaching quality increased the credibility of schools within their communities, encouraging greater enrolment and participation.

- Strengthened Organizational Capacity:

The parallel effort to upgrade digital platforms (such as website development) contributed to better communication, documentation, and outreach.

Overall Impact:

Development of stronger, more capable educational institutions that can sustain and build upon the project’s interventions.

Overall Outcome Perspective

The project outcomes demonstrate that integrated interventions—combining education, energy, health, and capacity building—can create a multiplier effect:

- Better infrastructure leads to better teaching

- Better teaching leads to better learning outcomes

- Improved health and hygiene lead to better attendance

- Reliable energy ensures continuity and sustainability

Together, these outcomes contribute to building a holistic, inclusive, and future-ready education ecosystem, benefiting students, teachers, and communities alike.

- IMPACT OVERVIEW

The School Infrastructure Project created meaningful and long-lasting impact across multiple domains by integrating education, energy, and community development. The interventions not only addressed immediate needs but also contributed to broader systemic improvements in rural and underserved areas.

  - Digital Learning Enhancement

The introduction of digital classrooms significantly transformed the way education is delivered and experienced in schools.

- Improved Learning Outcomes: Interactive digital content, including videos, animations, and subject-specific modules, helped simplify complex concepts. Students were able to visualize and understand topics more effectively, leading to improved comprehension and retention.

- Enhanced Classroom Engagement: Digital tools encouraged active participation, making classrooms livelier and more interactive. Students showed increased interest in attending classes and engaging with lessons.

- Exposure to Modern Teaching Tools: For many students, this was their first exposure to technology-enabled learning environments. This experience is crucial in preparing them for future academic and professional opportunities in an increasingly digital world.

- Teacher Transformation: Teachers shifted from traditional methods to facilitator-driven teaching, using digital tools to enhance lesson delivery and student interaction.

Overall Impact:

Creation of a modern, technology-enabled learning ecosystem that improves both teaching quality and student outcomes.

  - Rural Empowerment

The project played a significant role in strengthening rural education systems and reducing disparities.

- Strengthened Education Systems: By upgrading infrastructure and building teacher capacity, schools became more effective in delivering quality education.

- Bridging the Urban-Rural Digital Divide: Access to digital classrooms ensured that students in rural areas could benefit from learning tools similar to those available in urban schools, reducing inequality in educational opportunities.

- Increased Confidence Among Students: Exposure to technology improved students’ confidence, curiosity, and willingness to explore new learning methods.

- Community Confidence in Schools: Improved infrastructure enhanced the reputation of schools, encouraging greater trust and participation from parents and communities.

Overall Impact:

Empowered rural communities through improved access to quality education and modern resources, fostering inclusive development.

  - Sustainable Development

Sustainability was a key focus area, particularly through the integration of renewable energy solutions.

- Reduced Dependency on Grid Electricity: Activation of solar power systems ensured that schools are less affected by frequent power cuts, enabling consistent functioning.

- Environmentally Friendly Solutions: Use of solar energy contributes to reduction in carbon footprint, promoting environmentally responsible practices.

- Cost Efficiency: Over time, solar systems reduce electricity costs, allowing schools to allocate resources to other developmental needs.

- Long-term Infrastructure Benefits: Durable and sustainable solutions ensure that the benefits of the project continue well beyond the implementation period.

Overall Impact:

Promotion of clean energy adoption and long-term sustainability, benefiting both schools and the environment.

  - Community Well-being

The project extended its impact beyond schools to improve the overall well-being of communities.

- Improved Quality of Life for Elderly: Through healthcare interventions, elderly individuals received regular medical support, assistive devices, and access to welfare schemes, leading to better health and dignity.

- Strengthened Community Trust: Engagement with local communities built strong relationships and trust, ensuring support for project activities and sustainability of outcomes.

- Holistic Development Approach: By addressing both educational and health needs, the project contributed to overall community development, recognizing the interconnected nature of social challenges.

- Increased Community Participation: Communities became more involved in school activities and infrastructure maintenance, enhancing ownership and accountability.

Overall Impact: Creation of healthier, more engaged, and resilient communities, supporting long-term social development.

Overall Impact Perspective

The project’s impact areas highlight a multi-layered transformation:

- Students benefit from better learning opportunities

- Schools evolve into modern, resource-equipped institutions

- Communities experience improved health and stronger engagement

- Systems move towards sustainability and inclusivity

This integrated impact demonstrates that targeted infrastructure interventions, when combined with capacity building and community support, can lead to lasting and scalable change.

  - School Wise Direct Beneficiary:

| Sr. No | Name of the School | Intervention | No. of Students |
| --- | --- | --- | --- |
| 1 | ZP Primary School, Mandave Kh, Ahilyanagar | Installation of Digital learning solutions | 182 |
| 2 | ZP Primary School, Savargaon, Sangamner, Nashik | Installation of Digital learning solutions | 102 |
| 3 | ZP Primary School, Angapur No-2, Satara | Installation of Digital learning solutions | 84 |
| 4 | Mulakhore Vidyalay, Mandave Bk, Ahilyanagar | Installation of Incinerator for Girls | 288 |
| 5 | Yashwantrao Chavan Vidyalay, Bhosari, Pune | Solar System Repair & Activation | 180 |
| 6 | ZP Primary School, Kameri, Satara | Solar System Repair & Activation | 103 |
| 7 | New English School, Angapur, Satara | Solar System Repair & Activation | 285 |
| 8 | S. Anandrao Ghadge Vidyalay, Kameri, Satara | Solar System Repair & Activation | 118 |
| 9 | New English School, Chinchner Vandan, Satara | Solar System Repair & Activation | 175 |
| Total |  |  | 1,517 |

- TESTIMONIALS & CASE STUDY

TESTIMONIALS

“I would like to express my sincere gratitude to MASHAL for installing a sanitary napkin disposal unit in our school. This initiative has made a meaningful difference to our institution.

The facility has created a clean, safe, and dignified environment for our girl students. Earlier challenges related to hygiene and waste disposal have been effectively addressed. We are also seeing increased awareness about health, along with positive improvements in students’ confidence and attendance.

With this support, the overall infrastructure and basic amenities of our school have improved significantly, contributing to the holistic development of our students.

We are truly thankful for this initiative and look forward to continued support in the future.”

- Mr. Kharat Bhausaheb Maruti (Headmaster, Mulakhore Madhyamik Vidyalay, Mandave Budruk)

“We sincerely thank MASHAL for the Solar Repair & Activation initiative in our school. Earlier, the non-functional solar system affected our electricity supply and use of digital learning tools.

With the system now restored, we have a reliable power supply, enabling better use of e-learning resources and improved sanitation facilities.

This support has positively impacted the learning environment and overall quality of education in our school, especially in a rural setting.

We are truly grateful for this valuable intervention.”

- Mr. Dhanaji Katangale (Teacher, Z.P. School Kameri, Satara)

TESTIMONIALS

“We sincerely thank MASHAL for the Solar Repair & Activation initiative. Earlier, the non-functional solar system affected our daily operations and increased electricity costs.

With timely support, the system was repaired and is now running smoothly. We are seeing nearly 50% savings in electricity bills, and school activities continue without interruption, even during power outages.

This has significantly improved our school’s functioning and ensured uninterrupted learning for students.

We are grateful for this support.”

- Mr. Nitin Tonpe (Headmaster, New English School, Angapur, Satara)

“I would like to share our experience with the interactive panel provided by MASHAL. Introduced on Republic Day and currently used in our Grade 4 classroom, it has made learning more engaging, with students actively participating and understanding concepts faster. Lessons have become simpler and more enjoyable, and as teachers, we now guide students as they learn by doing.

Most of our students come from economically weaker backgrounds, and this digital tool has improved their confidence and overall learning experience. On behalf of our school, I sincerely thank MASHAL and assure that we will continue to use this resource effectively for our students’ future.”

-Dr. Balasaheb Shingote (Headmaster, ZP Primary School, Mandave Khurd, Parner, Ahmednagar)

Case Study

Background
Mulakhore Secondary School, Mandave Budruk (Taluka Sangamner, District Ahilyanagar), is situated in a rural area. The adolescent girls studying here faced numerous challenges related to menstrual hygiene management. Although the school possessed basic sanitation facilities, there was no mechanism available for the safe disposal of sanitary pads. Consequently, this led to increased feelings of hesitation, discomfort, and absenteeism among the female students.

Need
The absence of a proper disposal mechanism resulted in poor hygiene, health risks, and hesitation among girls, affecting their regular attendance and participation.

Intervention
MASHAL installed an incinerator machine (sanitary pad disposal unit) in the girls’ toilet, along with a solar power system to ensure reliable operation.

Implementation
The process included need assessment, selection of a suitable location, installation and testing of the unit, and awareness sessions on its safe use and hygiene practices.

Outcomes
The intervention enabled safe and hygienic disposal of sanitary pads, improved sanitation standards, and supported better health and well-being of students. It also contributed to increased attendance and participation among girls.

Impact
The initiative reduced stigma around menstruation, improved confidence, and created a more girl-friendly school environment while promoting eco-friendly hygiene practices.

Conclusion
The installation of an incinerator machine at Mulakhore Secondary School have created a clean, safe, and dignified environment for the girls. This initiative is not limited merely to sanitation; it has also had a positive impact on the students' health, self-confidence, and academic continuity. This serves as an effective and exemplary model for schools in rural areas.

Improving Menstrual Hygiene through Incinerator Installation

Mulakhore Secondary School, Mandave Budruk (Taluka Sangamner, District Ahilyanagar)

Case Study

Zilla Parishad Primary School, Angapur No. 2 (Taluka & District: Satara)

Enhancing Learning through Digital Smart Board Support

Background
At the Zilla Parishad Primary School, Angapur No. 2 (Taluka & District: Satara), teaching was being conducted using traditional methods. Students faced difficulties in grasping concepts, particularly in the subjects of Science and Mathematics. There was a distinct lack of digital tools.

Need
Students relied only on textbooks, struggled with abstract concepts, and showed low participation. Teachers also lacked effective tools for engaging instruction.

Intervention
MASHAL installed an Interactive Panel during the 2024–25 academic year, supported by e-learning content, subject-wise digital curriculum, and audio-visual tools.

Implementation
Teachers were guided on using the panel, which was regularly integrated into classroom teaching using digital content.

Outcomes
Students developed better conceptual understanding, and learning became more engaging. Participation improved, and teachers were able to deliver lessons more effectively, especially in subjects like Science and Environmental Studies.

Impact
Students showed increased interest in learning and adapted to digital methods. The overall school environment became more interactive, moving towards a “Digital School” approach.

Conclusion
The Interactive Panel initiative has proven to be highly effective for rural schools, resulting in a significant improvement in the quality of education. This initiative is well-suited for replication and implementation in other schools as well.

Legal Guidance for Property Security

Name: Hirabai Pandurang Pansare

Age: 75 years

Address: Jay Bhavani Nagar, Paud Road,

Kothrud, Pune – 411038

1. Background
Mrs. Hirabai Pansare has been residing in Jay Bhavani Nagar for the past 40 years. She has two sons and one grandson, who looks after her. She currently lives alone. It was her wish to transfer the ownership of her house to her grandson's name.

2. Problem Statement / Need
She required clear legal guidance to transfer her property, as she was unaware of the appropriate legal process and documentation.

3. Intervention / Initiative
Under the Vruddhamitra project, Community Organizer Megha Tai supported her with information and assistance. She attended a legal awareness session at Vitthal-Rukmini Temple, where her concern was discussed.

4. Implementation Process
Based on legal advice, it was clarified that a Gift Deed was not applicable for her property, and preparing a Will was the appropriate solution. She was then supported in accessing free legal consultation with an advocate.

5. Outcomes / Results
Hirabai understood the legal process and agreed to proceed with drafting her Will. The process is currently ongoing with continuous support.

6. Key Impact
The intervention ensured legal clarity, built confidence, and enabled her to make an informed decision regarding her property.

7. Conclusion
Through timely guidance and support, Hirabai is securing her grandson’s future as per her wishes. This case highlights the importance of legal awareness and support for senior citizens.

Case Study

Name: Subhadra Bhoskar

Age: 74 years

Address: Ramnagar, Bapuji Buwa Chowk,

Warje, Pune

Health and Financial Support through PMJAY Scheme

1. Background
Mrs. Subhadra Bhoskar, aged 74, resides with her family and has a history of high blood pressure. On January 19th, she suffered a stroke and was hospitalized, which created a significant financial burden on her family.

2. Problem Statement / Need
The sudden medical emergency led to high treatment costs, making it difficult for the family to manage expenses. There was also a lack of awareness about available government health schemes.

3. Intervention / Initiative
Under the Vruddhamitra project, Community Organizer Pallavi Tai guided the family about the PMJAY (Ayushman Bharat) scheme and supported them in applying for the card.

4. Implementation Process
During a home visit, the scheme and application process were explained. With continuous support, the family successfully obtained the PMJAY card, through which medical expenses of approximately ₹40,000 were covered.

5. Outcomes / Results
The financial burden on the family was significantly reduced. Subhadra Tai received timely medical treatment and continues to receive regular follow-up support, including health monitoring, diet guidance, and basic exercises.

6. Key Impact
The intervention improved access to healthcare, ensured financial relief, and supported her recovery. It also increased awareness and utilization of government health schemes.

Conclusion
This case highlights the importance of timely guidance and continuous support. Through the Vruddhamitra project, Subhadra Tai and her family were able to access essential healthcare services, leading to improved health and a stable situation.

Case Study

ANNEXURE I

PHOTO DOCUMENTATION

ZP Primary School, Mandave Khurd, Ahilyanagar

ZP Primary School, Savargaon, Ahilyanagar

ZP Primary School, Angapur No-2, Satara

Mulakhore Madhyamik Vidyalay Mandv Bk. Ahilyanagar

Yashwantrao Chavan Vidyalay, Bhosari, Pune

ZP Primary School, Kameri, Satara

S. Anandrao Ghadge Vidyalay, Kameri, Satara

New English School, Angapur, Satara

New English School, Chinchner Vandan, Satara

ANNEXURE II

Request And Completion Letters from School Headmasters

Completion Letter

Request Letter

ZP Primary School Mandave Khurd, Ahilyanagar

Completion Letter

Request Letter

ZP Primary School Savargaon, Nashik

Request Letter

Completion Letter

ZP Primary School Angapur No. 2, Satara

Request Letter

Completion Letter

Mulakhore Madhyamik Vidyalay Mandv Bk. Ahilyanagar

Request Letter

Completion Letter

Yashwantrao Chavan Vidyalay, Bhosari, Pune

Completion Letter

Request Letter

ZP Primary School, Kameri, Satara

Request Letter

Completion Letter

S. Anandrao Ghadge Vidyalay, Kameri, Satara

Request Letter

Completion Letter

New English School, Angapur, Satara

Completion Letter

Request Letter

New English School, Chinchner Vandan, Satara

ANNEXURE III

Audited Utilisation Certificate